LIFE Project Number

LIFE06 NAT/CZ/000121

PROGRESS REPORT No. 1

Covering the project activities from 1/1/2007 to 30/11/2007

Reporting Date

1/12/2007

LIFE PROJECT NAME

Preservation of alluvial forest habitats in the Morávka River Basin

Data Project

| Project location | Czech Republic, Moravian-Silesian Region |
| --- | --- |
| Project start date: | 1/1/2007 |
| Project end date: | 31/12/2010 |
| Total Project duration (in months) | 48 months |
| Total budget | 1.014.720 € |
| EC contribution: | 704.000 € |
| (%) of total costs | 69,38 % |
| (%) of eligible costs | 69,93 % |

Data Beneficiary

| Name Beneficiary | Moravskoslezský kraj (Moravian-Silesian Region) |
| --- | --- |
| Contact person | Mr. Tomáš Kotyza |
| Postal address | 28. října 117, 702 18 Ostrava |
| Visit address | 28. října 117, 702 18 Ostrava |
| Telephone | +420 595 622 387 |
| Fax: | +420 595 622 396 |
| E-mail | tomas.kotyza@kr-moravskoslezsky.cz |
| Project Website | http://www.life-moravka.cz |

# List of Contents and Annexes

Annex 1: Implementation of actions C.1, C.2 in January – November 2007

Annex 1A: Implementation of actions C.1, C.2 in January – November 2007 (detail A)

Annex 1B: Implementation of actions C.1, C.2 in January – November 2007 (detail B)

Annex 2: Implementation of actions D.1, F.4

Annex 3: Table of experimental plots

Annex 4: Information leaflet “Záchrana lužních stanovišť v povodí Morávky“ (Preservation of alluvial habitats in Moravka River Basin)

Annex 5: Preview of outdoor information panel

Annex 6: Map of location of outdoor information panels

Annex 7: Introductory page of www.life-moravka.cz

Annex 8: Photographic dokumentation

# Lists of (i) key-words and (ii) abbreviations (when appropriate)

- Elimination, spray, herbal injections, removing of dry biomass, river basin, invasive alien species, habitat, suppression, revitalization, herb layer,  planting of shrubs, outdoor information panels, water and soil monitoring, instructional tours, herbicide application, ceremonial start of the project

# Executive Summary (max 1 page)

The objectives of the project are consistent with “European strategy of invasive alien species”. The objectives are focused to pSCI Morávka river basin, partially pSCI Beskydy with focus on 8 habitats (out if which the priority 2 make in total 88% of the project site). The main objective of the project is being fulfilled in four areas:

- elaboration of efficient  methodology for suppression of invasive kinds and subsequent revitalization of the habitats.

- suppression of invasive Reynoutria in pSCI Morávka river basin as a needed postulate for rescue and recuperation of biodiversity.

- creation of  efficient transferable model of cooperation during problem solving in environmental protection amount the interested subjects on regional level

- project results spreading and providing further information on Natura 2000 and environmental protection generally on  the local, regional, state and international levels.

The project execution can be considered positive within the reporting period (1.1.–30.11.2007), covering nearly the whole first project year. There were no serious problems found that would be able to influence both the course and the objectives of the project in negative way, all actions planned for the relevant period have been fulfilled (nearly entirely in demanded scope) and partners involvement was adequate to the project plan and demands.

Thirteen actions of total eighteen have been fully or partly carried out until now.

The following actions have been executed above the expectation in comparison with the project plan for the relevant period:

- C.2 Revitalization of herb layer of selected habitats (provision of sufficient amount of seed in compliance with demands on genetic originality, starting co-operation with the experienced body, execution of a pilot sowing at the scope of more than 10 000 square meters).

- C. 3 Planting of original species of shrubs (consultation with bodies experienced in the topic including pre-negotiation of the potential execution of the action).

- E.1 Information leaflet “Niva Morávky, a Site Important on European Level and Natura 2000 System“ (the printing increased from 5 000 to 10 000 pieces to ensure distribution to each household within the project area).

- E.3 "PSCI Niva Morávky" educational CD-ROM (comprehensive activities focused on data collection and adopting the new type of media to be used – documentation of the project execution by video)

- E 8 Websites of the project, "Preservation of alluvial forest habitats in Morávka river basin” (extension of the Web site content and provision of the English version)

- F.2 Coordination of project PR activities (extension of media presentation including statutory and private television on the national level, ceremonial official start of the project, extended information distribution to all municipalities and public of the project area).

- F.4 Monitoring of the impacts of project activities (regular monthly monitoring, higher number of indicators used in water monitoring).

The following actions have been executed in line with the project plan for the relevant period:

- D.1 Research of “Optimisation of invasive species and subsequent revitalization of habitats” (higher number of experimental plots however not in all various ecotypes, increasing of number of mechanical methods tests.

- E.6 Outdoor information panels

- F.1 Project Management

The following actions have not been executed in line with the project plan for the relevant period:

- C.1 Elimination of Reynoutria spp. (not applied to 18 ha from 200 ha totally planned from the reason of herbicide delivery delays – see chapter 5)

- E.4 Instructional tours to pSCI Niva Morávky (lower number of instructional tours in the first year – the higher number is planned for the following project years)

- E.5 Workshops for local community (lower number of seminars in comparison with the plan corresponding with lower demand – possibility of increasing the number of workshops in the following project years)

It can be stated from the point of view of the budget use that it complies with the project plan (i.e. submitted application). Budget items have been used proportionally taking into consideration the project time schedule (11 months from 48 ones = 22,9 % project course). There are following exceptions: „Consumable Materials“ (98,9%), which had to be bought at the project start and „Other costs“ (audit,  0%), which will be used at the end of the project on the contrary.

Two fields of activities should be highlighted as positive on the basis of the project team evaluation and/or numbers of responds to intentions, course and partial results of the project:

1) Complex scientific solution of invasive species suppression including methods testing and detailed monitoring of herbicide application impacts, 2) PR activities – especially communication with municipalities and public in the project area, media presentation and ceremonial start of the project with the positive responds, project field presentations – systematically dislocated attractive information panels.

Taking into consideration experience with the first eleven months of the project course we would highlighted the following key items for the next year: a quantity of Reynoutria spp. elimination made by this year actions (to be known in May 2008 – there exists possibility to increase capacities for the fieldwork), higher focus on revitalization of habitats by sowing of plants and shrubs, continuing positive results of project impacts monitoring (i.e. realization of action C.1 without negative environmental impacts) and keeping high level of project PR activities (including extension of communication outside Moravian-Silesian region and also to scientific public).

- Technical development

A	 Preparatory actions/management plan preparation

There are no actions falling into this category in the project.

B	Land purchase

There are no actions falling into this category in the project.

C	Non-recurring biotope management

There are three actions falling into this category in the project. These actions were executed within the relevant period as follows:

C.1 Reynoutria spp. elimination

Plan:

Ten percent solution of Roundup will be sprayed to an area of 190 ha, where the coverage of Reynoutria is high. The herbicide will be sprayed on young plants. Older, more grown plants will be mowed first, and only then the herbicide will be sprayed on the recovering plants, which will reduce the amount of Roundup used. The average consumption expected is 13 l of Roundup per ha.

In an area of 10 ha showing lower Reynoutria coverage, the herbicide (5 ml of 15% solution of Roundup Biaktiv) will be injected to herbs’ nodes. The average consumption expected is 56 l per ha.

The action will be implemented by 8 workers + 2 team chiefs, the equipment used will include 10 sprayers, 10 brush cutters and 2 cars, all for 8 months (the team chiefs will be employed for 10 months), plus external aid.

Execution:

The preparatory phase was executed before the fieldwork start including the following steps:

- Elaborate Reynoutria spp. methodology draft (including discussion on elimination possibilities with partners, etc…): January - May

- Elaborate land owners map and gain permissions of land owners for activities on land with Reynoutria spp.:  January - May

- Divide the project area according to competence of project partners: January - May

- Elaborate emergency plan elaboration, train staff: January - July

- Ensure permissions for activities in protected areas: January - June

- Buy machines and other tools for fieldwork (brush-cutters, sprayers, blower sprayers, protective means): March - April

Fieldwork concerning Reynoutria spp. elimination was running in the following parts of the relevant period:

- Mowing of grown plants before herbicide application: 23.4. - 17.7.

- Herbicide application to plants (spraying, injection): 19.7. - 11.10.

- Mowing and transporting dry biomass out of the area: 15.10 – 30.11.

There were mowed 54 ha of Reynoutria spp. totally before the start of herbicide application. Two different solution concentration were used for spraying. 7% solution of Roundup (decreased concentration on the base of supplier recommendation taking into the consideration also risks for environment made by herbicide use in such large area – it has been sufficient for Reynoutria spp. elimination and simultaneously more environmental friendly. 10 % solution of Roundup (according to the management plan for the new National Natural Monument, simultaneously it is a concentration include in the project application). 126 ha of Reynoutria spp. were sprayed once in 2007, other 47 ha twice (the second application was originally planned for the next year) – i.e. spray was applied to 173 ha totally. The plan has not been reached (17 ha not sprayed = less than 10 % of the plan). The reasons were shortening time of the spray because of the problems included in the chapter 5 (especially delays in herbicide delivery, shortening the season by early start of freeze). It is expected to be compensated next year without problems since time suited for the spray will be used fully next year (herbicide has been ensured yet for the next year). The average consumption of herbicide was 12,5 l/ha, it means in 0,5 l/ha lower in comparison with the plan.

10% solution in comparison with the planned 15% solution was used for injections according to the recommendation of the supplier – it has been sufficient for Reynoutria spp. elimination and simultaneously more environmental friendly. A quantity was used according to the project application (5 ml). Injections were applied twice at the area of 2,5 ha, i.e. totally at 5 ha. It means the plan has not been reached (10 ha planned). There were three reasons for it: the new mwthod was used to be tested within the project; primarily areas with high presence of Reynoutria spp. were treated this year – the spray method is more suitable for such areas generally; injections were especially planned for areas upstream Morávka reservoir – these activities will be realized in the next year. Injections method will be more used in the next year and it is expected to be compensated by the extended application the next year reaching the plan objectives. The average consumption of herbicide was 24 l/ha, it means in 32 l/ha (57%) lower in comparison with the plan.

Above mentioned activities were implemented 10 workers + 2 team chiefs, the equipment used  included 5 sprayers, 5 blower sprayers (as alternative to an use of sprayers), 10 brush cutters and 2 cars, all for 8 months (the team chiefs for 10 months). An external aid of all project partners competent to the action was used. It should also be said to complete the picture the Roundup Biaktiv package return duty has been included into the contract of purchase. Herbicide package has been eliminated ecologically according to the valid legislation.

Field activities (determination of areas to be treated and methods of elimination to be used, timing of activities) were coordinated by the scientific coordinator (in cooperation with team chiefs) and they were evaluated by the scientific coordinator subsequently (especially taking into consideration their effects and surrounding biota. Project manager and assistant were continuously informed on all facts.

Overview of C.1 action is enclosed in annexes 1, 1A, 1B.

C.2 Revitalization of herb layer of selected habitats

Plan:

Firstly genetic originality of seed must be maintained. Because of these reasons only material originated in the area of the project area shall be used. With regard to shortage of this material other shall be collected directly in pSCI Niva Morávky . These seeds shall be used for direct sowing on target areas and for creation of parental growth for production of seed utilizable in the following years.

The sowing shall be performed in all areas where Reynoutria before elimination showed coverage of 50 % or higher, and - if it  is desirable - also in other areas. The realization shall be performed immediately after the elimination of Reynoutria and removal of its dead biomass, and - if necessary - also in subsequent years. We will start with the sowing in early summer (VI.-VII.) of the second year of the project in areas where the Reynoutria elimination will be successful. 2 gr of seed per m2 shall be used; the composition of species shall include 5 species of grass and 7 species of herbs.

Execution:

The action is subsequent to Reynoutria spp. elimination and transport of dead trunk out of the area. Since the transport is still running currently (and it will probably be running during the whole winter on the base of weather conditions, the action was planned especially for 2. - 4. project year)

The company Oseva Pro Ltd. based in Zubří was selected to cooperate within this action. This company has been participating successfully in projects dealing with cultivation and sowing native species of plants for several years. It has produced several tens of genetically original plants from beskydy region from this reason. There had been selected 12 habitat adequate species: 9 species of grass and 3 species of herbs. Action was realized on sites, where Reynoutria spp. had been eliminated successfully at the total area 1,1 ha in the past (between project application submission and the project start). The sowing was realized on November 5.

Collection of other species seeds in pSCI Niva Morávky,  including creation of parental growth is planned for the following years.

Overview of C.2 action is enclosed in annexes 1, 1A, 1B.

C.3 Planting of original species of shrubs

There were consultations with several bodies experienced in similar activities as a preparatory part of the action. Results include a.o. a promise of cooperation including the action realization to be started in spring 2008.

D	Recurring biotope management

There is one action falling into this category in the project. This action was executed within the relevant period as follows:

D.1 Research of “Optimisation of invasive species and subsequent revitalization of habitats”

Plan:

- Establishment of experimental plots in various ecotopes (various types of forests, green fields, grit drifts in various sun exposures, etc.). The use of several tens of experimental surfaces are foreseen (at least 36), at the size of 10 – 30 m2 each. The Scientific coordinator will control the experimental plots at least twice a month (or more if necessary).

- Investigation into the use of various concentrations of herbicides (4 – 15 %) on parts of the experimental surfaces within the experimental habitats. Application the herbicide on whole plants and on mechanically destroyed plant (combination mech.+chem. method) as well.

- Use of the procedures set forth under point 2 in all months of the Reynoutria growing season (May – October) in order to find out when the application is the most effective.

- Investigations into other (more cautious) methods, such as herbicide injections into the node, application to a chopped-off stem, lifting of rootstock, etc. Testing on surfaces set forth under 1), testing of efficacy during the entire Reynoutria growing season (each month from May to October).

- Verification of the best method of restoring of the biotope after the intervention, especially through herb sowing and shrub planting  (testing the rate at which the plants renew if sowed immediately after the intervention/in autumn months after the completion of the total Reynoutria eradication/the next year in the spring; testing the efficiency of spring and autumn sowings).

The final results of the research will be, after processing of foreign procedures, incorporated in the methodology of controlling invasive Reynoutria.

Execution:

The research plan was established before the start of the action execution. It was consulted with the monitoring team manager and some changes as the result of these consultations were made: higher emphasis on testing of non-chemical methods, lowering the number of tested concentrations of Roundup Biaktiv, tests of other similar kinds of herbicides.

Realization of individual steps wa as follows:

- There were 48 experimental plots in size of 10 m2 established on May 31. One set of plots was established in forest. The second one was established on green fields. Young grit drift have not been included into the research because all of suitable ones lay within the new established National Natural Monument (NNM) and it would not be adequate to use this area with strict protection for experiments like that. Phytosociological survey (i.e. overview of species and their distribution) had been elaborated before tests. Experimental plots were checked by scientific coordinator twice per month, eventually more often – changes found were recorded.

- In harmony with the project plan the following activities were applied to experimental plots: Roundup Biaktiv plants spray of 5 and 10 % concentration, Dominátor spray of 4 and 8% concentration and Glyfoganspray of  5 and 10 % concentration.

- Spray was applied in different time during the period July – September (time will be extended next year yet).

- In harmony with the resesarch plan the following activities were applied at the experimental plots: Roundup Biaktiv application to a chopped-off stem of 50 % solution of herbicide and injections of 50 and 100 % Roundup Biaktiv solutions. Non chemical measures: mowing twice a year and lifting of rootstock were realized in July and August.

- In harmony with the research plan the following actions were realized at the experimental plots:  sowing of grass-herb mixture (5.11., 10 species totally  – 8 species of grass and 2 species of herb)

Experimental plots localization is enclosed in annex 2, exact time of tests realization including their localization to experimental plots is presented in annex 3.

Invasive Reynoutria spp. working version method was also elaborated in cooperation with all competent partners. This method has created a base for issue to be published and distributed during the international conference.

E	Public awareness and dissemination of information

There are nine actions falling into this category in the project. These actions were executed within the relevant period as follows:

E.1 Information leaflet “Niva Morávky, a site important on European level and Natura 2000 system“

Plan:

An information leaflet will be produced in A3 format, triple-folded (final format cca 100x205mm), both sides printed, in colour, including English summary, number of copies will be 5,000 (to be reprinted in case of need). It will be distributed free of charge in offices, schools, during project activities (seminars, conferences, instructional tours etc.) via partners etc., and it will be available for download (free of charge) from the project websites in PDF format. The image part of the leaflet will constitute 40 %, the textual part will contain information about the territory, important ecosystems and species, about project goal and expected results. Information about project holder and partners will also make part of the leaflet in the extent of 25 % of the overall content.

The content of the leaflet will be processed within the frame of activities F.1 and F.2.

Execution:

Information leaflet was produced on April 4, including the following parameters: A3 format, triple-folded (final format cca 100x205mm), both sides printed, in colour, from the content point of view in harmony with the project plan, including English summary. Number of copies has been increased from 5,000 to 10,000 from the reason of higher demand (distribution to each household in the relevant area – see action E.5.). The content of the leaflet was processed within the frame of activities F.1 and F.2 (project manager, assistant and scientific coordinator in cooperation with PR manager). Leaflet was distributed to partners, municipalities and also used in the framework od other project activities (seminars, project presentations) since April 4 and since it has also been available for download (free of charge) from the project websites in PDF format, link: http://www.life-moravka.cz/doc/letak_life_moravka.pdf.

Leaflet is enclosed in annex 4.

E.2 The information leaflet “Preservation of alluvial forest habitats in Niva Morávky, a site important on European level“

Action was not planned nor realized in the relevant period.

E.3 PSCI Niva Morávky" educational CD-ROM

Plan:

Production of CD-ROM has been planned for the fourth year of the project, which would contain maximum of information not only about pSCI Niva Morávky, but also about other significant territories of Natura 2000, important species of plants and animals in the territory of the Czech Republic, importance and problems of environmental protection in general etc. It would be focused on 8th and 9th class of elementary and secondary schools as an additional learning text for regional geography and natural history education but its practical usability will be much wider.

Execution:

There were primarily preparation activities realized this year especially collection of text and picture source materials. It also was decided the CD-ROMu would also contain video presentation focused on presentation of natural heritage of the area, nature protection including Natura 2000 as well as project course and results. There are several hundreds of photos and tens of scientific text pages prepared (both partly used for the presentation at the project Web site yet) as well as nearly 3 hours of video records (fiels activities and records of all project actions in 2007).

E.4 Instructional tours to pSCI Niva Morávky

Plan:

In the period from April to October instructional tours to pSCI Morávka will be organized. These educational tours are primarily targeted to students of elementary and secondary technical schools. They will also be organized for other groups : community representatives, representatives of professional organizations or  general public. Concrete educational tours will be realized according to visitors´ request by PR coordinator in cooperation with scientific coordinator. An educational tour in the occasion of Day of Earth will be organized regularly every year. The estimated overall number of educational tours is 10 a year, it won’t be any problem to increase their number in case of need.  The estimated number of participants of one single tour is 20 to 30 people.

Execution:

There were organized 2 instructional tours this year (11.9.). First of them was targeted to public administration representatives from the whole Moravian-Silesian region, who are responsible for nature protection which also means responsibility for invasive species suppression. The second one was targeted for municipalities representatives (especially mayors) both of the relevant area and from the surooundings. The project presentation, its current results and problems of invasive plant species in general were discusses at the instructional tours. Moreover results of Reynoutria spp elimination were presented in the field including objective examples of elimination methods, among other rather rarely used (such as injections).

Instruction tours attendance was unfortunalety lower than expected because of bad weather (strong rain), which is difficult to forecast in this mountain region. Educational tours for children from schools of relevant area in spring and a tour in the occasion of Earth Day are also planned.

E.5 Workshops for local community

Plan:

Local inhabitants shall be invited to the workshops where the project shall be presented in detail and the necessity of intervention shall be explained. At the same time, they shall be made familiar with the problems of invasive plants. The lectured topics shall include hazards of invasive plants to the local nature, methods of foreign plants dissemination, possibilities of eliminating the invasion. They shall also be briefed in the system of NATURA 2000 protection. Further, they shall be asked for involvement into the project by simple monitoring and passing of information regarding Reynoutria spp. occurrence in their surrounding.

Private landowners will be specifically targeted and invited to co-operate in the Reynoutria eradication. All inhabitants concerned with Reynoutria spp. elimination shall be invited to the workshops through posters, local broadcasting and press. Specifically, the following villages are under question: Dobrá, Nošovice, Nižní a Vyšní Lhoty, Raškovice, Pražmo, Morávka and Krásná.

The local inhabitants shall be informed about the project interim results in the local press and regional media continuously. Seminars will be organized by PR coordinator in cooperation with the scientific coordinator.

Similar seminars focused on identical topics will be organized in local elementary and secondary schools. Amusing form to present key topics will be used.

Execution:

Two seminars for local public were organized on 7.6. and 13.6. (i.e. before Reynoutria spp. chemical elimination start): one in Dobrá, the second in Raškovice. Compared to the project plan not all 8 seminars were organized at the project beginning, but it had been decided to organize 2 seminars per year to brief participants about recent developments of the project. Morever public of the relevant area had been informed about the project objectives and starting activities before the first set of the seminars (extending the project plan by that) by: articles in all local municipal newsletters (distributed to all households), delivery of project information leaflet (distributed also to all households), informations on municipality official boards as well on other suitable places, a letter on planned Reynoutria spp. elimination targeted especially to landowners, etc…

Project was presented to seminars participants especially the necessity of Reynoutria spp. elimination was highlighted (including the necessity to use herbicide). They were also informed about problems of invasive plant species in general, nature protection in relevant area including Natura 2000. Participants were also asked to participate directly with the project team: lists of plots where an existence of Reynoutria spp. was indicated were given to all municipalities to enable inhabitants to check whether their plot (with Reynoutria spp. presence) included. If not they had possibilities to notify the plot with Reynoutria spp. found (both own one and/ore owned by somebody else).

It can be stated generally, according to immediate feedback, intentions of the project have been accepted very positively: Reynoutria spp. has been considering a serious, difficult and increasing problem with negative impacts not only to environment but also to value of inhabitants property for tens of years. The project team was sent by several tens of lots, not included before, with the indication of Reynoutria spp. existence to be involved into the project actions. .

E.6 Outdoor information panels

Plan:

Outdoor information panels (30 units – 100 x 80 cm) shall be installed at the points of entry into the project area. The information panels shall be made of sheet metal on a wooden column fixed in the ground. The information panels location is designed in the map. The text in the tables shall inform about the project in progress, its importance for the local and European nature. The panel shall include basic information on NATURA 2000 system, LIFE logo and a brief summary in English language.

Execution:

Outdoor information panels had been produced in harmony with the project plan and subsequently installed (14. – 19.6.). Map of information panels is enclosed as annex 6, preview of outdoor panel is available on the project Web site, link: http://www.life-moravka.cz/doc/info_tabule.pdf.

Picture of the panel is enclosed as annex 5.

E.7 International conference "Invasive alien species of plants"

Action was not planned nor realized in the relevant period.

E.8 Websites of the project, "Preservation of alluvial forest habitats in Morávka river basin”

Plan:

For the purpose of informing the general public and sharing experience websites specialising in the field of invasive plants with focus on Reynoutria spp. will be prepared. The main presented topic will be how to proceed in eliminating Reynoutria spp. in the Moravka river basin. The history of plant invasion, impacts of the invasion on nature, methods of liquidation and prevention possibilities represent other topics of the websites. The websites will be used for the presentation of individual partners and other activities of participating subjects as well. Last but not least the websites will discuss the issues of the financial tool, LIFE and NATURA 2000 system with focus on local areas of European importance.

The PR coordinator will be responsible for putting the websites in operation and i their update. In realization of this project he will cooperate with project assistant and scientific coordinator.

Execution:

Czech version of the project Web site have been put into operation in at the date of the project ceremonial start (see action F.2), i.e. 28.2.2007, link: www.life-moravka.cz. Website contains the following information topics: information on the project, current news, partners, gallery, page with files to be downloaded, links, contacts, etc… There are links to all project partners home pages as well as to Programme Life and Natura 2000 addresses. There also exist internal part of the Web site which is available only to project partners using specific password. Internal documents (such as draft documents to be discussed, documents for the Management Committee, recent projrct plan, elimination methods, emergency plan, etc…).

Web site is being regularly updated by the project manager assisstent under guarantee of the PR manager. Cooperation with project manager and scientific coordinator is regularly requested. Recently the English version of the Web site has been put into operation on the base on DG Environment recommendation (since 15.11.).

Other topics, such as history of plant invasions, invasion impacts to nature, ways of suppression, prevention possibilities are expected tro extend the Website in near future.

First Web page copy www.life-moravka.cz is enclosed as an annex 6.

E.9 Layman Report

Action was not planned nor realized in the relevant period.

F	Overall project management

There are five actions falling into this category in the project. These actions were executed within the relevant period as follows:

F.1 Project Management

Plan:

Successful realisation of the whole project is guaranteed by the project manager, especially in the  following areas:

- Management of the project. Setting up a draft of the action plan, controlling its realization, suggesting its modification. Assembling, coordination and preparing the quarterly reports submitted to the management committee (the committee will meet at least four times a year). Submitting monthly reports to the members of the committee.

- Coordination. PM co-ordinates proper participation of all partners, activity of the members of the realisation team and activity of the Committee for the invasive species, all in cooperation with the scientific coordinator. PM proposes changes under the participation of relevant partners based on actual needs; provides job description of each position, possibly also changes in the structure of the project team.

- Monitoring and controlling. Systematic controls of the preparation, realization and evaluation of all project actions and fulfilment of the time schedule; especially regular checks of the  realization of the fieldwork in cooperation with other members of  the Committee. Checking the fulfilment of the job by individual project team members is also included. Supervising the project manager as far as gathering of supporting documents releted to the LIFE project is concerned.

Assistant prepare, coordinate or provide data for the project manager. Supervising the management of the project, preparing, realizing and evaluating all activities, primarily from the management point of view, in cooperation with partners, the scientific coordinator, the PR activity manager. She is in regular personal touch (at least twice a week) with the scientific coordinator, PR activity manager and the chief of the working team. Partial problems are flexibly fixed together with them. Graphical outputs dissemination is provided in cooperation with the PR manager. One of the tasks of the project assistant will be to form a database of subjects and projects realized in the field of the suppression of invasive species worldwide. This list will be updated every year and then sent to subjects mentioned in the list. The database of subjects and projects realized in the area of invasive species suppression (groundwork for distributing project results to the Czech Republic and abroad, provision of erudite attendance when organizing the international conference, etc.) will be formed in co-operation with the scientific coordinator. The Project assistant directly participates in the realization of actions in case of work overload of the project manager, the PR activity manager or the scientific coordinator. For the sake of traceability of expenditure and income, an analytical accounting system (cost centre accounting) shall be established by the beneficiary and partners. The beneficiary will keep all appropriate supporting documentation for all expenditure, income and revenue for the project as reported to the Commission, such as invoices, purchase orders, proofs of payments, salary slips, time sheets and any other documents used for the calculation and presentation of costs. The copies of all documents related to the LIFE project will be gathered by PA on a regular (e.g. monthly) basis from all the participants. The frequency will be agreed in the project partnership agreement.

The Scientific coordinator will ensure regular monitoring of potential negative impacts (F4) of the course of action C1, and he will fluently modify the procedure. The activity described as Monitoring of impacts of project activities (F4) will be ensured by the Committee for invasive species in cooperation with the scientific coordinator. This activity is connected with all activities within this project, but for better clarity it is possible to calculate all costs within F1.

The scientific coordinator will work part-time during the whole realization of the project. He will be directly subordinated to the project manager and in general issues he will cooperate with the project assistant. In further solving of scientific problems he will cooperate with the committee for invasive species and with the advisory board for invasive species. He will also be a supervisor and scheduler of interventions leading to the Reynoutria control. He will create the elimination plan including  time schedule, as well as the method of elimination used in respective parts of the project area. In this case he will be the mediator between the project manager and working groups. In cooperation with PR coordinator he will participate in the realization of activities E1 to E9.

Creating the methodology of experiments as the first step in this action, on the basis of which he proposes (determines the area and time), controls, modifies and evaluates the realization of specific interventions. Working out of annual reports for the Commission for invasive species and coordinates the commission activities. Participating in the working-out of quarterly reports for the management committee. Coordinating activities of the Supervisory board for invasive species, ensuring information transfer in both directions (i.e. between the project realization staff and other Czech and foreign subjects actively dealing with suppressing invasive species). Guaranteeing the professional quality of graphic outputs and taking part in organising other PR activities. He is a specialist that guarantees the international conference, as well as an expertly worked-out Methodology of invasive plant elimination.

The supreme authority in the project management will be the management committee.  It will consist of 8 members (representative of the beneficiary plus seven members representing all the partners). The management committee will meet three times a year, or more frequently in case of need. Its main task will be to pass yearly proposal of the realization of project activities and yearly evaluation of realized activities. Sufficient knowledge and awareness of the committee will be provided for by the project manager, with the support of the project assistant.

The main task of the Committee for invasive species is to optimise the procedure of the Reynoutria suppression based on actual results of the field work. The Commission suggest, in case of need, methodical changes in the activities C1, C2, C3. It will consist of six members, i.e. all the partners dealing with the suppression of invasive species will have a professionally competent representative in the body. The committee will meet or visit the place of realization of the project according to need, it will be informed each month about the progress of realization by the project manager. The results of the work of the scientific coordinator will also make part of this information.

Advisory board for invasive species will be another, less formalized body, whose task will be to provide for information flow within the frame of invasive species suppression issues. Its members will be representatives of Czech and foreign organizations dealing with elimination of invasive species. The task will be permanent exchange of current experience, the communication will be provided mainly by e-mail. Another task of the advisory board will be to co-operate in providing for attendance and scientific content of the international conference.

Execution:

Project Manager:

- Project Management: Annual project plan was setting up and regularly updated;  Quarterly project plans were setting up and regularly updated; 4 meetings of the Management Committee were organized (31.1., 4.4., 27.6. a 17.10.) – Management Committee was informed on project performance, fulfilling of quarterly plans, eventual changes, and other aspects of the project execution by quarterly reports; Management Committee also approved draft quarterly plans for the next quarters; other more recent information were not formalized and included in the report, but it was given to MC members (in case of need) and/or to other interested persons continuously.

- Coordination: Active participation of partners, activities of project team members as well as activities of committee for invasive species were coordinated in cooperation with the scientific coordinator; simultaneously several minor changes to the project were proposed to be taken into consideration and/or to be approved by the MC; job description of each position including minor changes in the scope of competence of project team members were made at the beginning of the project.

- Monitoring and controlling: PM was involved into realization of all project activities either directly or at the consultation and/or approval levels to ensure a harmony with the planned time schedule or to avoid potential delays would not influence a course and results of the project; regular checks of the realization of the fieldwork were done (usually once a week); checking the fulfilment of the job by individual project team members were also done continuously, including as far as gathering of supporting documents releted to the LIFE project is concerned..

Project assistant closely cooperated with the PM especially by preparing and providing actual data to him. She furthmore, being a Beneficiary representative, supervised the project management, preparing, realizing and evaluating all activities, in cooperation with partners, the scientific coordinator and the PR activity manager. She was the key person participating in preparation and ratification of partner contracts at the project beginning. In cooperation with the PR activity coordinator she were preparing ceremonial project start, media campaign, leaflet distribution, updating of the project Website and communication with municipalities and land owners in the relevant area. Communication with monitoring team representatives and directly to European Commission was also in her competence.

Database of subjects and projects realized in the field of the suppression of invasive species worldwide was also prepared by the project assistant in cooperation with the scientific coordinator. For the sake of expenditure and income control, an accounting system was established by the beneficiary and partners. Archive of supporting documentation for all expenditure, income and revenue for the project (such as invoices, purchase orders, proofs of payments, salary slips, time sheets) was established as a part of it. The copies of all documents (or their copies) were gathered by PA on a quarterly basis, an overview of income and expenditure was prepared on a monthly basis.

First of all the scientific coordinator has created the elimination plan before the field work start, including territorial competence of partners, time schedule of work, as well as the method of elimination used in respective parts of the project area. The scientific coordinator created a research plan and system of potential negative impacts monitoring in connection with it. She coordinated execution of all above mentioned activities, eventually she directly participated in it as well as she drafted and/or approved potential changes of procedures.

The scientific coordinator also cooperated with other project team members especially in information leaflets and panels content elaboration, project Web site preparation and seminar organization. She further coordinated Commission for invasive species and, in cooperation with the Project Manager also the Advisory board for invasive species. She participated in quarterly reports for Management committee preparation. Recently she is elaborating annual report 2007 for Commission for invasive species.

Management committee consists of 7 members (compared to 8 ones planned – from the reason of abdication of 1 partner during the period of the project approval), representatives of the beneficiary  and all the partners. The management committee met four times officially in 2007 (31.1., 4.4., 27.6. a 17.10.) and during ceremonial project start. There were also many individual meetings of the project team and partners representatives. Committee approved the annual project plan and four quarterly project plans.

Commission for invasive species consists of six members, i.e. all the partners dealing with the suppression of invasive species had a professionally competent representative in the body.  Commission had three meetings in 2007 (31.1., 4.4., 22.7.), moreover there were several tens of individual meetings project team members with the commission members held. Communication is maintained also by e-mail and phone. Main commission activities were as follows: territorial division of area to competence of partners (for reynoutria spp. elimination), consultation on elimination methods use (in harmony with limited factors – for example to drinking water sources, management plan of protected areas), prepareation and execution of tenders on service suppliers, etc...

Advisory board for invasive species (AB) has been another, less formalized body, which consists of 12 members, representatives of both Czech and foreign organization dealing with invasive species elimination. AB members were informed on the project and there were severel tens of individual consultations of project team with AB members held (personally, by e-mail and phone). There was a meeting with U.K. company TCM R(D on February 28. The company deals with Reynoutria spp. elimination (as well as other invasive species) not only in U.K. Project team members as well as partners representatives were introduced to company´s experience in the problems of invasive species solution. Company representatives were informed about project intentions (including field visit). Mutual communication has been functioning since the meeting, the planned autumn visit of the company representatives to get know about the first project year results has been postponed to spring 2008.

Annual report being recently elaborated by the scientific coordinator will be sent to Advisory Board members, too. Currently a working version of the invasive species elimination method is being elaborated valid for the whole Czech republic.

F.2 Coordination of project PR activities

Plan:

The coordinator of project PR will be working part time during the whole period of the project. His job will be to provide for the successful realization of E.1.-9. activities. Apart from the above-mentioned activities the PR coordinator will be in charge of long-term campaign in media on local, regional, national and international level. In carrying his duties he will cooperate mainly with the scientific coordinator and with the project assistant. Being directly subordinated to the project manager, he will also cooperate with the advisory board to a certain extent. The coordinator guarantees dissemination of all graphic outputs and updating of the websites. He documents project implementation.

Execution:

PR activities manager elaborated information and communication strategy at the beginning of the project execution. The strategy proposes a system of communication between all project stakeholders as well as a system of the project presentation. He participated in the preparation and organization of the ceremonial project start, including the press conference, together with the project assistant. He also coordinated project media presentation – he elaborated press report, prepared and corrected articles in periodicals, etc… He further participated in preparation and elaboration of all actions of part E: in cooperation of other project team members: E.1. Information leaflet “Niva Morávky, a site important on European level and Natura 2000 system“;  E.4 Instructional tours to pSCI Niva Morávky; E.5 Workshops for local community; E.6. Outdoor information panels and E.8 Websites of the project, "Preservation of alluvial forest habitats in Morávka river basin”

F. 3 : Independent final report audit

Action was not planned nor realized in the relevant period.

F.4 Monitoring of the impact of project activities

Plan:

The main aim of this action is to monitor impacts the application of the product, Roundup Biaktiv on sensitive and important herb and animal species. The first step will be creation of a comprehensive methodology in co-operation with Czech universities. The methods of monitoring shall be approved by the Committee for invasive species. The main feature of the monitoring will be the observation of changes in biota (damage, dieback), but also monitoring of the load on soil and water, including background monitoring. We will use non-destructive methods. The monitoring will be performed by independent experts, e.g. experts from universities or research organisations. It is planned that the monitoring should be initiated in March-April 2007. The conclusions of the monitoring, and possible findings of any damage to the environment or biota, shall be incorporated in the method of Reynoutria elimination, which shall be modified so that no damage could occur in future. It will be reflected in action C.1.

Execution:

Impacts monitoring plan was elaborated before start of monitoring in the field. It involved a.o. identification of chemical analysis methods, draft on sampling sites selection and sampling timing was proposed. This document was elaborated in cooperation with VŠB TU from the beginning, however the cooperation had not aimed to the concrete results it has been changed subsequently to other bodies: project partner Povodí Odry, state company and other subjects: OKD - DPB  (branch ekotechnika), Ekotoxa, Ltd., Institute of Geo-Sciences (Geonika) Czech Academy of Science. The document was elaborating between January and June.

Subsequently suppliers of individual parts of monitoring (biota, water and soil) were selected by tendering. It has been also decided together with Povodí Odry to enable use of its data on water monitoring, being gathered within its own operation, for purposes of the project continuously. Above mentioned activities were executed between March and June.

Monitoring itself began on April 18, when the phytocenological survey was started (so called background monitoring of biota). Biota monitoring was kept till October 11. Water monitoring began on June 25 (so called background monitoring carried out also on July 9, yet). Further monitoring was carried out in the following dates: 18.7., 30.7., 27.8., 24.9., 18.10. and 29.10.). Water samples were taken at 9 profiles being determined on the basisi of agreement with Povodí Odry. Account was taken on the following indicators in harmony with the project application: N-(phosphonometyl)-glycine, AMPA (Amino-methyl-phospone acid). Moreover the account was taken on the following indicators on the basis of the agreement with Povodí Odry:  pH, chemical oxygen consumption, oxygen, phosphates, total phosphorus. Background monitoring of soil was executed on July 15, other sampling was done on 21.8. a 30.10. Soil samples were taken in 5 profiles – mixture sample was created by 9 individual samples taken in each of profiles.

All samples analyzed within the project monitoring were negative even when using the most exact analysis – it means all monitoring results (water, soil, biota) were under the limit of distinction. The above mentioned results were found even in situation when sampling of biota and soil were done just at sites of herbicide application and/or water sampling was carried out just after the spray was applied in the highest level. From the reason above there was no reason until now to modify the Reynoutria spp. elimination method.

Overview of monitoring sampling sites is enclosed in annex 2.

F.5 After-life Conservation Plan

Action was not planned nor realized in the relevant period.

# 5.  Problems encountered

There were no serious problems found during the project execution that would be able to influence both the course and the project objectives in negative way. Potentially there could be one problem identified: According to the Mosanto company information, the Roundup Biaktiv producer, the herbicide should be withdrawn from the market in 2007 – the project team would be faced the necessity to ensure an adequate environmental friendly substitution in such a case. It was decided after further negotiations it can be solved by buying sufficient amount of the herbicide in advance (among other quite easy because of the amount necessary to reach the project goals).

Despite of the absence of serious problems there were several minor problems found that had impacts to project tasks timing eventually they demanded increase effort of the project team.  The following ones can be introduced:

  - Ensuring delivery Roundup: beside the above mentioned problem there was another complication with the herbicide purchase – the first (June 22) tender had to be cancelled (on the base of the State Phytosanitary Administration impuls; it has been fount the winner had not fulfilled conditions concerning permission on import this herbicide to CR); the second tender was finished on June 28, which influenced delay of the firs herbicide delivery to July 13 and delay of herbicide application in the field in 3 weeks by that.

  - Creation of working teams: despite of the competent partner intention (having been declared in the project application) to employ local employees it was found it was not possible (without regards to intensive communication to the relevant Employment Office there were no persons with interest to be employed by the project available. That´s why employees were ensured at the competent partner location. Subsequently several changes at working team posituon were made (including one working team chief), however personal constitution in June, i.e. before the main fiel work start, was stabilized.

  - Major part of pSCI Niva Morávky was proclaimed as national natural monument during the period between the project application submission and the project start – it mens more strict regime for the project execution in the area in general. It means in practice the higher effort of the project assistant and project coordinator during the project execution.

  - Shortening the working season by unfavourable weather: The first freeze started sooner than usually in this area this year, which made impossible to use the standard length of the season at least nor its entension which would be needed from the reason of chemical methods application start delays. .

# 6.  Financial issues

PROJECT COSTS INCURRED

|  |  | Cost category | Total cost according to the Commission’s decision* | Total costs incurred from the start date to 30.11.2007 | %** |
| --- | --- | --- | --- | --- | --- |
| 1. |  | Personnel | 441 640 | 71 293 | 16,1 |
| 2. |  | Travel | 42 180 | 9 601 | 22,8 |
| 3. |  | Outside assistance | 261 900 | 46 627 | 17,8 |
| 4. |  | Durables: total cost | 16 100 | 15 923 | 98,9 |
| 5. |  | Land purchase | 0 | 0 |  |
| 6. |  | Consumables | 177 500 | 33 525 | 18,9 |
| 7. |  | Other costs | 5 000 | 0 | 0 |
| 8. |  | Overheads | 70 400 | 10 990 | 15,6 |
|  |  | SUM TOTAL | 1 014 720 | 187 958 | 18,5 |

*) or, if there has been an additional clause with budget modification, to the revised budget included in that additional clause

**) Calculate the percentages by budget lines: How many % of the budgeted personnel costs are incurred by xx.xx.xxxx

# 7.  Planned project progress

C	Non-recurring biotope management

10% solution of Roundup will be sprayed to an area of 350 ha, where the coverage of Reynoutria is high. The herbicide will be sprayed on young plants. Older, more grown plants will be mowed first, and only then the herbicide will be sprayed on the recovering plants, which will reduce the amount of Roundup used. The average consumption expected is 13 l of Roundup per ha.

In an area of 10 ha showing low Reynoutria coverage, the herbicide (5 ml of 15% solution of Roundup Biaktiv) will be injected to herbs’ nodes. The average consumption expected is 56 l per ha.

The action will be implemented by 8 workers + 2 team chiefs, the equipment used will include 10 sprayers, 10 brush cutters and 2 cars, all for 8 months (the team chiefs will be employed for 10 months), The external aid will also be used

Unlike the project application content Roundup will be sprayed to other area of 17 ha and injected to 5 ha (not fulfilled part of the plan for 2007). In case of need the capacity for this key project year will be increased (gigher number of teams members and chiefs, equipment, etc…)

C.2 Revitalization of herb layer of selected habitats

Sowing will be provided at the areas where Reynoutria spp. had showed canopy closure at the level 50 % and/or more, eventually at other areas. There will continue intensive consultations with cooperating subject Oseva Pro Ltd. during January – April to draft complex solution of the Action in significantly higher scope with maximized effectiveness of results. Sowing is planned immediately after Reynoutria spp. elimination and transport of dead plants, i.e. since June. There will be used 2 g of seed for sowing per m2, consisiting of 12 herbs as minimum.

The task to ensure genetically original seed will be continuously kept. From this reason only local seed will be used. Practcally only genetically original material produced by Oseva Pro Ltd. will be used, but the other procedures will be used: sowing of seeds of hay from local grass fields and sowing of local seed obtained by collection. A part of seed collection will also beused for the parental growths creation.

C.3 Planting of original species of shrubs

1500 shrubs at the area of 21 ha is planned to be planted totally during the whole project course (it depends on the actual stock prize). The following species are planned to be planted: Cornus sanguinea, Euonymus europaea, Ligustrum vulgare, Salix caprea a Salix purpurea. It was decided to plant shrubs in the period March – May in the second year of the project with regard to decrease possibility of potential young shrubs demage by the herbicide application.

There were consultations with several bodies experienced in similar activities as a preparatory part of the action. Results include a.o. a promise of cooperation including the action realization. Cuttings from suitable trees will be obtaind in the relevant area in February – March, major part of them will be planted out to selected sites in March – April, minor part used for planting of stocks (to be used for potential subsequent planting in case they will not survive). There are 300 individuals of Salix caprea and Salix purpurea planned to be planted to the area of 6 ha in 2008. To avoid damage of plants by game they will be protected by coat (Aversol etc.). Plants will be replaced in autumn in case they will not survive. The other species as included in the project application and other plants will be planted in last two project years to lower, a.o. risks of their damage by herbicide.

D	Recurring biotope management

D.1 Research of “Optimisation of invasive species and subsequent revitalization of habitats”

There will be the first longer term results of research at the experimental plots available next year (Reynoutria spp. elimination, sowing). On the basis of these results the methods testing will be continuing in harmony with the research plan. Chemical and mechanical methods of elimination and sowing will be applied and as a new mwthod planting will be tested. All tests results will be recorded and analyzed, eventually they will be used for the elimination methodology modification.

E	Public awareness and dissemination of information

E.1 Information leaflet “Niva Morávky, a site important on European level and Natura 2000 system“

Distribution of the leaflet will be continuing the whole year especially during the special actions, in case of need for the partners, municipalities, schools, etc… needs as well.

E.2 The information leaflet “Preservation of alluvial forest habitats in Niva Morávky, a site important on European level“

Execution of this action has not been planned for the year 2008.

E.3 PSCI Niva Morávky" educational CD-ROM

Execution of this action is planned for the fourth year of the project. Collection of pictures, video shots and texts will continue in 2008 as a preparatory part of the action.

E.4 Instructional tours to pSCI Niva Morávky

Significantly extension of the action is planned in 2008 compared to 2007. In spring instructional tours to students and teachers of local schools are planned as well as instructional tour connected to Earth Day. In summer, eventually in autumn instructional tours are planned focused on Reyounitra spp. elimination methods presentation (including subsequent care) as well as project course presentation. There are 10 tours planned as minimum.

E.5 Workshops for local community

Two workshops for local community are planned for 2008 (the same as in 2007), in the period May – June. In case of higher interest it is possible to increase the number of workshops and/or to target them more specifically (e.g. to possible procedures on Reynoutria spp. elimination at minor land owners plots).

E.6 Outdoor information panels

Action was realized in 2007, in case of need (panels damage) the panels will be repaired or substituted.

E.7 International conference "Invasive alien species of plants"

Action has not been planned for 2008.

E.8 Websites of the project, "Preservation of alluvial forest habitats in Morávka river basin”

Web site will be maintained and updated continuously.

E.9 Layman report

Action has not been planned for 2008.

F	Overall project management

F.1 Project Management

All project position will be kept in harmony with the project plan (according to the project application) as well as with the course of 2007 (see description in the chapter 4). Four meetings of the Management Committee and a meeting of the Commission for invasive species are planned for the year as well as individual consultation with their members in case of need. Extended communication is planned with Advisory Boars for invasive species is planned focused especially on cooperation in Invasive species elimination draft methodology valid for the whole CR elaboration.

F.2 Coordination of project PR activities

This action will also be executed in line with the one in 2007 (see description in the chapter 4). Extended project media presentation is planned, especially in connection to the first longer term results of Reynoutris spp. elimination (as well as subsequrnt habitats revitalizations) and to new activities realization.

F. 3 : Independent final report audit

Action has not been planned for 2008.

F.4 Monitoring of the impact of project activities

Action will be executed in 2008 at the same level and regime as in 2008 with the following extensions: the sooner monitoring start in connection to the sooner beginning of Reynoutria spp. elimination action and and new actions monitoring in the framework of biota monitoring, specifically actions C.2 and C.3 (sowing herbs and planting shrubs).

F.5 After-life Conservation Plan

Action has not been planned for 2008.

# 8.  Annexes

Annex 1: Implementation of actions C.1, C.2 in January – November 2007

Annex 1A: Implementation of actions C.1, C.2 in January – November 2007 (detail A)

Annex 1B: Implementation of actions C.1, C.2 in January – November 2007 (detail B)

Annex 2: Implementation of actions D.1, F.4

Annex 3: Table of experimental plots

Annex 4: Information leaflet “Záchrana lužních stanovišť v povodí Morávky“ (Preservation of alluvial habitats in Moravka River Basin)

Annex 5: Preview of outdoor information panel

Annex 6: Map of location of outdoor information panels

Annex 7: Introductory page of www.life-moravka.cz

Annex 8: Photographic dokumentation